## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate(hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a admission desk executive /pharmacist/ diagnostic center executive I want to be able to log in the hospital website with my user ID and password So that I carry out my transactions | Task 1 | Komal | Write a program for displaying the home page | 4 | 2 | 2 | 0 |  |  |  | Closed
|  | Task 2 | Komal | Design the UI for the Login page | 4 | 2 | 0 |  |  |  |  | Closed
|  | Task 3 | Abhishek | Design and create the DB fields for Executive, Pharmacist & Diagnostic | 4 | 3 | 2 | 0 |  |  |  | Closed
|  | Task 4 | Abhishek | Direct each of the users to their respective pages | 3 | 3 | 2 | 1 | 0 |  |  | Closed
|  | Task 5 | Abhishek | Perform session management to avoid access of pages without proper login credentials. | 4 | 4 | 3 | 2 | 0 |  |  | Closed
|  | Task 6 | Abhishek | Test the working for each type of user | 3 | 3 | 3 | 2 | 1 | 0 |  | Closed
US002 | As a admission desk executive I want to be able to capture new patient information So that I can create a new patient in the system | Task 1 | Komal | Write program to display the patient registation page | 4 | 3 | 1 | 0 |  |  |  | Closed
|  | Task 2 | Komal | Design the UI for the patient registation page | 3 | 2 | 0 |  |  |  |  | Closed
|  | Task 3 | Rohan | Take input fields from the executive | 3 | 2 | 1 | 0 |  |  |  | Closed
|  | Task 4 | Sukrut | Create a new patient record and add all the information | 4 | 4 | 3 | 2 | 0 |  |  | Closed
|  | Task 5 | Chinmayi | Generate a unique Patient ID which is to be assigned to the new patient | 3 | 3 | 3 | 3 | 0 |  |  | Closed
|  | Task 6 | Rohan | Test the working for valid and unvalid patient fields data | 3 | 3 | 3 | 3 | 2 | 0 |  | Closed
US003 | As a admission desk executive I want to be able to edit existing patient information So that I can store the updated patient information in the system | Task 1 | Komal | Write program to display the patient update page | 4 | 2 | 2 | 1 | 0 |  |  | Closed
|  | Task 2 | Kamlesh | Design the UI for the patient update page | 5 | 3 | 2 | 0 |  |  |  | Closed
|  | Task 3 | Rohan | Search for the patient from the input Patient ID | 4 | 3 | 3 | 2 | 0 |  |  | Closed
|  | Task 4 | Kamlesh | Display existing information of the respective patient | 4 | 4 | 3 | 2 | 1 | 0 |  | Closed
|  | Task 5 | Kamlesh | Update the fields which are edited and save the new details of the patient in the database. | 6 | 6 | 4 | 2 | 0 |  |  | Closed
|  | Task 6 | Rohan | Test the working for valid and unvalid patient ID | 4 | 4 | 4 | 3 | 2 | 0 |  | Closed
|  | Task 7 | Kamlesh | Test whether the changes are reflected in the table of database | 4 | 4 | 4 | 4 | 2 | 0 |  | Closed
US004 | As a admission desk executive I want to be able to delete existing patient from system | Task 1 | Kamlesh | Write program to display the patient delete page | 4 | 2 | 3 | 0 |  |  |  | Closed
|  | Task 2 | Komal | Design the UI for the page | 3 | 1 | 0 |  |  |  |  | Closed
|  | Task 3 | Rohan | Search for the patient from the input Patient ID | 3 | 2 | 0 |  |  |  |  | Closed
|  | Task 4 | Sukrut | Delete the patient details from the Database | 4 | 4 | 2 | 0 |  |  |  | Closed
|  | Task 5 | Chinmayi | Test the working for valid and unvalid patient ID | 3 | 3 | 2 | 0 |  |  |  | Closed
|  | Task 6 | Abhishek | Test whether the patient details are deleted from database | 3 | 3 | 2 | 0 |  |  |  | Closed
US005 | As a admission desk executive I want to be able to view all the active patients currently admitted in the hospital | Task 1 | Kamlesh | Write program to display the view patient page | 4 | 3 | 0 |  |  |  |  | Closed
|  | Task 2 | Komal | Design the UI for the page | 3 | 0 | [5 empty] | Closed
|  | Task 3 | Sukrut | Search for the patients which are currently admitted to the hospital | 3 | 3 | 1 | 0 |  |  |  | Closed
|  | Task 4 | Abhishek | Display all the patients admitted with required data fields | 3 | 3 | 3 | 3 | 2 | 0 |  | Closed
US006 | As a admission desk executive I want to be able to search for a patient So that I am able to view the details | Task 1 | Chinmayi | Write program to display the patient search page | 4 | 2 | 2 | 1 | 0 |  |  | Closed
|  | Task 2 | Abhishek | Design the UI for the search page | 3 | 2 | 2 | 0 |  |  |  | Closed
|  | Task 3 | Sukrut | Search for the patient from patient ID | 4 | 3 | 2 | 2 | 0 |  |  | Closed
|  | Task 4 | Kamlesh | Display all the required data field of the patient if ID exists or else display an error message | 3 | 3 | 2 | 2 | 0 |  |  | Closed
US007 | As a pharmacist I want to be able to capture the medicines issued to a patient So that I can issue new medicines for an existing patient | Task 1 | Kamlesh | Write program to display the pharmacist page | 5 | 4 | 2 | 0 |  |  |  | Closed
|  | Task 2 | Komal | Design the UI for the pharmacist page | 4 | 3 | 1 | 0 |  |  |  | Closed
|  | Task 3 | Kamlesh | Search for the patient from patient ID | 6 | 6 | 5 | 5 | 3 | 0 |  | Closed
|  | Task 4 | Rohan | Display all the issued medicines for the patient | 7 | 7 | 6 | 6 | 3 | 2 | 2 | Closed
|  | Task 5 | Komal | Provide an option to issue new medicines to the patient from Master Medicine Database | 4 | 4 | 4 | 4 | 3 | 3 | 3 | In Progress
|  | Task 6 | Chinmayi | Reduce the stock quantity of provided medicines | 4 | 4 | 4 | 4 | 3 | 3 | 3 | In Progress
|  | Task 7 | Komal | After this is done update these medicines to the Issued Mesdicines record of the current patient | 3 | 3 | 3 | 3 | 3 | 2 | 2 | In Progress
|  | Task 8 | Kamlesh | Check during search whether the patient ID is valid | 4 | 4 | 4 | 2 | 0 |  |  | Closed
|  | Task 9 | Kamlesh | Check during issuing new medicine whether the medicine is available | 3 | 3 | 3 | 3 | 0 |  |  | Closed
US008 | As a diagnostics executive I want to be able to capture the diagnostics conducted to a patient So that I can add new tests for an existing patient | Task 1 | Komal | Write program to display the diagnostic page | 5 | 3 | 2 | 0 |  |  |  | Closed
|  | Task 2 | Komal | Design the UI for the diagnostic page | 4 | 2 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Sukrut | Search for the patient from patient ID | 6 | 5 | 5 | 4 | 3 | 0 |  | Closed
|  | Task 4 | Rohan | Display all the tests conducted for the patient | 7 | 7 | 7 | 7 | 5 | 3 | 0 | Closed
|  | Task 5 | Chinmayi | Provide an option to conduct new tests to the patient from Master Diagnostic Database | 4 | 4 | 4 | 4 | 4 | 4 | 3 | In Progress
|  | Task 6 | Kamlesh | After this is done update these tests to the tests record of the current patient | 4 | 4 | 4 | 4 | 4 | 4 | 4 | In Progress
|  | Task 7 | Kamlesh | Check during search whether the patient ID is valid | 3 | 3 | 3 | 3 | 2 | 0 |  | Closed
|  | Task 8 | Kamlesh | Check during test prescibed whether the test is available in the hospital | 4 | 4 | 4 | 3 | 2 | 2 | 0 | Closed
US009 | As a admission desk executive I want to be able to get existing patient information So that I can raise the bill for the patient | Task 1 | Chinmayi | Write program to display the billing page | 4 | 3 | 4 | 4 | 4 | 3 | 0 | Closed
|  | Task 2 | Komal | Design the UI for the billing page | 3 | 1 | 0 |  |  |  |  | Closed
|  | Task 3 | Sukrut | Search for the patient from patient ID | 4 | 4 | 2 | 0 |  |  |  | Closed
|  | Task 4 | Chinmayi | Calculate the bill for accomodation | 4 | 4 | 4 | 4 | 4 | 2 | 0 | Closed
|  | Task 5 | Chinmayi | Calculate the bill for pharmaceutical charges | 4 | 4 | 4 | 4 | 4 | 3 | 0 | Closed
|  | Task 6 | Chinmayi | Calculate the bill for diagnostic services | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Closed
|  | Task 7 | Chinmayi | Calculate the Total Bill | 4 | 4 | 4 | 4 | 3 | 2 | 0 | Closed
|  | Task 8 | Chinmayi | Change the status of patient from 'Active' to 'Discharged' | 4 | 4 | 4 | 4 | 4 | 4 | 3 | Closed
Back End Story | Creation of databases,Tables, validification of form fields,Session Management | Task 1 | Abhishek | Creation of Database for Login,Patient Registration Page | 3 | 2 | 2 | 0 |  |  |  | Closed
|  | Task 2 | Sukrut | Creation of Tables for View, Search and Update Pages handled by desk executive. | 3 | 2 | 2 | 1 | 0 |  |  | Closed
|  | Task 3 | Chinmayi | Creation of Master Tables for Medicine List, Diagnostics List. | 4 | 3 | 1 | 0 |  |  |  | Closed
|  | Task 4 | Chinmayi | Creation of Tables for Issued Medicines and diagnostics conducted. | 4 | 4 | 3 | 3 | 3 | 0 |  | Closed
|  | Task 5 | Abhishek | Password Validification and Form Field Validators | 3 | 3 | 2 | 3 | 3 | 2 | 0 | Closed
|  | Task 6 | Abhishek | Session Management for Login | 3 | 3 | 3 | 3 | 2 | 1 | 0
|  | Task 7 | Abhishek | Documentation | 3 | 3 | 3 | 3 | 3 | 2 | 0 | Closed
[5 empty] | 250 | 211 | 172 | 123 | 78 | 45 | 20

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
250 | 210 | 165 | 120 | 75 | 35 | 0
250 | 211 | 172 | 123 | 78 | 45 | 20